## Team Overview
AG ONE — Team Overview Dashboard 2026
All teams at a glance • Updated: Sprint 7 (current)
Team / Product | Tech Lead | Team Size | Members | Current Sprint | Sprint Goal | Status | Key Blocker
🏆 MILESTONE: Sprints 1–6 Complete — MVP successfully launched for AG ONE, OneWork, Learn & Safe 🚀
AG ONE | Geena | 2 | Geena, Nastaran | Sprint 7 | Post-launch stabilisation & monitoring | On Track
OneWork | Abdullah | 4 | Abdullah, Nastaran, Jawad, Geena | Sprint 7 | Post-MVP enhancements & user feedback | On Track
Learn | Ricky | 3 | Ricky, Loc, Than | Sprint 7 | Post-MVP enhancements & user feedback | On Track
Safe | Faisal | 3 | Faisal, Surya, Kiritini | Sprint 7 | Post-MVP enhancements & user feedback | On Track
OneHire | Logesh | 4 | Logesh, Hanis, Fatin, Sharuti | Sprint 1 |  | Not Started
Spot | Ricky | 5 | Ricky, Loc, Than, Majed, Hema | Sprint 1 |  | Not Started
Pulse | Hanis | 6 | Hanis, Fatin, Majed, Hema, Rahmya, Umeshawar | Sprint 1 |  | Not Started

## Resource Allocation
Resource Allocation Matrix — 2026
Shows which member belongs to which team • Shared resources highlighted
# | Member | AG ONE | OneWork | Learn | Safe | OneHire | Spot | Pulse | Total Teams | Availability % | Notes
1 | Abdullah |  | ✓ | [5 empty] | 1 | 100%
2 | Faisal |  |  |  | ✓ |  |  |  | 1 | 100%
3 | Fatin |  |  |  |  | ✓ |  | ✓ | 2 | 50% | Shared
4 | Geena | ✓ | ✓ | [5 empty] | 2 | 50% | Shared
5 | Hanis |  |  |  |  | ✓ |  | ✓ | 2 | 50% | Shared
6 | Hema | [5 empty] | ✓ | ✓ | 2 | 50% | Shared
7 | Jawad |  | ✓ | [5 empty] | 1 | 100%
8 | Kiritini |  |  |  | ✓ |  |  |  | 1 | 100%
9 | Loc |  |  | ✓ |  |  | ✓ |  | 2 | 50% | Shared
10 | Logesh |  |  |  |  | ✓ |  |  | 1 | 100%
11 | Majed | [5 empty] | ✓ | ✓ | 2 | 50% | Shared
12 | Nastaran | ✓ | ✓ | [5 empty] | 2 | 50% | Shared
13 | Rahmya | [6 empty] | ✓ | 1 | 100%
14 | Ricky |  |  | ✓ |  |  | ✓ |  | 2 | 50% | Shared
15 | Sharuti |  |  |  |  | ✓ |  |  | 1 | 100%
16 | Surya |  |  |  | ✓ |  |  |  | 1 | 100%
17 | Than |  |  | ✓ |  |  | ✓ |  | 2 | 50% | Shared
18 | Umeshawar | [6 empty] | ✓ | 1 | 100%

## Project Roadmap
Project Roadmap & Delivery Targets — 2026
Track start/end, achievements, next targets, and delivery alignment
Team / Product | Project Name | Start Date | Target End | Current Phase | Achieved So Far | Next Target | Delivery Aligned? | Risk / Blocker | Owner
AG ONE | AG ONE Platform | 05 Jan 2026 | 31 Dec 2026 | Post-MVP | ✅ MVP launched (Sprint 6) — Users, Roles, Tenants, SSO, Permissions, Audit, Assign Access all live | Platform hardening, advanced analytics, multi-product admin | Yes |  | Geena
OneWork | OneWork Platform | 05 Jan 2026 | 31 Dec 2026 | Post-MVP | ✅ MVP launched (Sprint 6) — Employee mgmt, workflows, task mgmt, dashboards all live | Advanced workflows, integrations, reporting v2 | Yes |  | Abdullah
Learn | Learn LMS | 05 Jan 2026 | 31 Dec 2026 | Post-MVP | ✅ MVP launched (Sprint 6) — Courses, learning paths, assessments, certifications all live | Advanced analytics, content marketplace, mobile support | Yes |  | Ricky
Safe | Safe Compliance | 05 Jan 2026 | 31 Dec 2026 | Post-MVP | ✅ MVP launched (Sprint 6) — Policies, compliance tracking, audit workflows, risk matrix all live | Regulatory updates automation, advanced reporting, third-party integrations | Yes |  | Faisal
OneHire | Recruitment Portal | 02 Feb 2026 | 31 Jul 2026 | Not Started |  |  | Yes |  | Logesh
Spot | City Module | 02 Mar 2026 | 30 Nov 2026 | Not Started |  |  | Yes |  | Ricky
Pulse | Survey Analytics | 16 Feb 2026 | 31 Aug 2026 | Not Started |  |  | Yes |  | Hanis

## Sprint Tracker
Sprint-by-Sprint Tracker — 2026
Record goals, outcomes, tech lead feedback, and blockers every sprint
Team | Sprint | Dates | Sprint Goal | Achieved | Tech Lead Feedback | Achievement / Win | Failure / Miss | Blocker | Status
AG ONE | Sprint 1 | 05 Jan – 18 Jan | Platform architecture & project setup | Project scaffolding, CI/CD pipeline, auth foundation | Strong start — clean architecture established | Architecture approved by all tech leads | — | — | ✅ Completed
AG ONE | Sprint 2 | 19 Jan – 01 Feb | User management & role system core | Users CRUD, Roles CRUD, permission matrix API | Solid delivery — core IAM features ready | Role-based permission engine live | — | — | ✅ Completed
AG ONE | Sprint 3 | 02 Feb – 15 Feb | Tenant management & SSO integration | Tenant settings, SSO middleware, API key management | SSO complexity handled well | Multi-tenant SSO working end-to-end | — | — | ✅ Completed
AG ONE | Sprint 4 | 16 Feb – 01 Mar | Assign Access wizard & user-role assignment | 3-step Assign Access wizard, bulk role assignment, pre-check | UI matches Figma perfectly | Assign Access wizard shipped with all edge cases | — | — | ✅ Completed
AG ONE | Sprint 5 | 02 Mar – 15 Mar | Audit logs, login history & polish | Audit trail, login history, pagination, UI polish | Production-quality output | Full audit & compliance features delivered | — | — | ✅ Completed
AG ONE | Sprint 6 | 16 Mar – 29 Mar | MVP launch — AG ONE platform go-live | ✅ MVP LAUNCHED — AG ONE platform live for all tenants | Excellent execution — platform launched successfully | 🚀 AG ONE MVP successfully launched! | — | — | ✅ Completed
AG ONE | Sprint 7 | 30 Mar – 12 Apr | [6 empty] | ▶ In Progress
AG ONE | Sprint 8 | 13 Apr – 26 Apr
AG ONE | Sprint 9 | 27 Apr – 10 May
AG ONE | Sprint 10 | 11 May – 24 May
AG ONE | Sprint 11 | 25 May – 07 Jun
AG ONE | Sprint 12 | 08 Jun – 21 Jun
AG ONE | Sprint 13 | 22 Jun – 05 Jul
AG ONE | Sprint 14 | 06 Jul – 19 Jul
AG ONE | Sprint 15 | 20 Jul – 02 Aug
AG ONE | Sprint 16 | 03 Aug – 16 Aug
AG ONE | Sprint 17 | 17 Aug – 30 Aug
AG ONE | Sprint 18 | 31 Aug – 13 Sep
AG ONE | Sprint 19 | 14 Sep – 27 Sep
AG ONE | Sprint 20 | 28 Sep – 11 Oct
AG ONE | Sprint 21 | 12 Oct – 25 Oct
AG ONE | Sprint 22 | 26 Oct – 08 Nov
AG ONE | Sprint 23 | 09 Nov – 22 Nov
AG ONE | Sprint 24 | 23 Nov – 06 Dec
AG ONE | Sprint 25 | 07 Dec – 20 Dec
AG ONE | Sprint 26 | 21 Dec – 31 Dec
OneWork | Sprint 1 | 05 Jan – 18 Jan | OneWork module setup & core data models | Project structure, DB schema, base API endpoints | Good foundation — aligned with AG ONE architecture | Schema aligned with platform on day 1 | — | — | ✅ Completed
OneWork | Sprint 2 | 19 Jan – 01 Feb | Employee management core features | Employee CRUD, search, filters, list views | Clean implementation, reusable components | Component library started for reuse | — | — | ✅ Completed
OneWork | Sprint 3 | 02 Feb – 15 Feb | Workflow engine & task management | Workflow builder, task assignment, notifications | Workflow engine exceeded expectations | Dynamic workflow engine working | — | — | ✅ Completed
OneWork | Sprint 4 | 16 Feb – 01 Mar | Dashboard & reporting module | Manager dashboard, team views, KPI widgets | Dashboards look great — director-ready | Real-time KPI dashboard shipped | — | — | ✅ Completed
OneWork | Sprint 5 | 02 Mar – 15 Mar | Integration testing & bug fixes | End-to-end testing, 42 bugs fixed, perf optimization | Thorough testing — production ready | Zero critical bugs in final round | — | — | ✅ Completed
OneWork | Sprint 6 | 16 Mar – 29 Mar | MVP launch — OneWork go-live | ✅ MVP LAUNCHED — OneWork live for all tenants | Flawless launch — team delivered on time | 🚀 OneWork MVP successfully launched! | — | — | ✅ Completed
OneWork | Sprint 7 | 30 Mar – 12 Apr | [6 empty] | ▶ In Progress
OneWork | Sprint 8 | 13 Apr – 26 Apr
OneWork | Sprint 9 | 27 Apr – 10 May
OneWork | Sprint 10 | 11 May – 24 May
OneWork | Sprint 11 | 25 May – 07 Jun
OneWork | Sprint 12 | 08 Jun – 21 Jun
OneWork | Sprint 13 | 22 Jun – 05 Jul
OneWork | Sprint 14 | 06 Jul – 19 Jul
OneWork | Sprint 15 | 20 Jul – 02 Aug
OneWork | Sprint 16 | 03 Aug – 16 Aug
OneWork | Sprint 17 | 17 Aug – 30 Aug
OneWork | Sprint 18 | 31 Aug – 13 Sep
OneWork | Sprint 19 | 14 Sep – 27 Sep
OneWork | Sprint 20 | 28 Sep – 11 Oct
OneWork | Sprint 21 | 12 Oct – 25 Oct
OneWork | Sprint 22 | 26 Oct – 08 Nov
OneWork | Sprint 23 | 09 Nov – 22 Nov
OneWork | Sprint 24 | 23 Nov – 06 Dec
OneWork | Sprint 25 | 07 Dec – 20 Dec
OneWork | Sprint 26 | 21 Dec – 31 Dec
Learn | Sprint 1 | 05 Jan – 18 Jan | Learn module setup & LMS architecture | Module scaffold, course data model, API skeleton | Clean start — well-structured codebase | LMS data model approved | — | — | ✅ Completed
Learn | Sprint 2 | 19 Jan – 01 Feb | Course management & content builder | Course CRUD, content upload, module builder | Content builder is intuitive | Drag-and-drop content builder working | — | — | ✅ Completed
Learn | Sprint 3 | 02 Feb – 15 Feb | Learning paths & assignments | Learning path creation, auto-assignment rules, progress tracking | Assignment logic is solid | Auto-assignment engine completed | — | — | ✅ Completed
Learn | Sprint 4 | 16 Feb – 01 Mar | Assessment engine & certifications | Quiz builder, grading, certificate generation | Assessment engine works perfectly | Certification flow end-to-end | — | — | ✅ Completed
Learn | Sprint 5 | 02 Mar – 15 Mar | UI polish, testing & launch prep | UI refinements, integration tests, launch checklist done | Ready for production | All acceptance criteria passed | — | — | ✅ Completed
Learn | Sprint 6 | 16 Mar – 29 Mar | MVP launch — Learn go-live | ✅ MVP LAUNCHED — Learn live for all tenants | Smooth launch — great team effort | 🚀 Learn MVP successfully launched! | — | — | ✅ Completed
Learn | Sprint 7 | 30 Mar – 12 Apr | [6 empty] | ▶ In Progress
Learn | Sprint 8 | 13 Apr – 26 Apr
Learn | Sprint 9 | 27 Apr – 10 May
Learn | Sprint 10 | 11 May – 24 May
Learn | Sprint 11 | 25 May – 07 Jun
Learn | Sprint 12 | 08 Jun – 21 Jun
Learn | Sprint 13 | 22 Jun – 05 Jul
Learn | Sprint 14 | 06 Jul – 19 Jul
Learn | Sprint 15 | 20 Jul – 02 Aug
Learn | Sprint 16 | 03 Aug – 16 Aug
Learn | Sprint 17 | 17 Aug – 30 Aug
Learn | Sprint 18 | 31 Aug – 13 Sep
Learn | Sprint 19 | 14 Sep – 27 Sep
Learn | Sprint 20 | 28 Sep – 11 Oct
Learn | Sprint 21 | 12 Oct – 25 Oct
Learn | Sprint 22 | 26 Oct – 08 Nov
Learn | Sprint 23 | 09 Nov – 22 Nov
Learn | Sprint 24 | 23 Nov – 06 Dec
Learn | Sprint 25 | 07 Dec – 20 Dec
Learn | Sprint 26 | 21 Dec – 31 Dec
Safe | Sprint 1 | 05 Jan – 18 Jan | Safe module setup & compliance framework | Module scaffold, policy data model, compliance engine design | Compliance model is comprehensive | Compliance framework designed and approved | — | — | ✅ Completed
Safe | Sprint 2 | 19 Jan – 01 Feb | Policy management & data library | Policy CRUD, version control, data library foundation | Policy versioning is well thought out | Policy versioning system live | — | — | ✅ Completed
Safe | Sprint 3 | 02 Feb – 15 Feb | Compliance tracking & audit workflows | Compliance checklist, audit trail, automated reminders | Audit workflow exceeds requirements | Automated compliance reminders working | — | — | ✅ Completed
Safe | Sprint 4 | 16 Feb – 01 Mar | Reporting & compliance dashboard | Compliance dashboard, risk matrix, export reports | Dashboard is director-ready | Risk matrix visualization shipped | — | — | ✅ Completed
Safe | Sprint 5 | 02 Mar – 15 Mar | Integration testing & security hardening | Security audit passed, pen test fixes, perf tuning | Security standards met — production ready | Passed security audit with zero critical findings | — | — | ✅ Completed
Safe | Sprint 6 | 16 Mar – 29 Mar | MVP launch — Safe go-live | ✅ MVP LAUNCHED — Safe live for all tenants | Outstanding delivery — launched on schedule | 🚀 Safe MVP successfully launched! | — | — | ✅ Completed
Safe | Sprint 7 | 30 Mar – 12 Apr | [6 empty] | ▶ In Progress
Safe | Sprint 8 | 13 Apr – 26 Apr
Safe | Sprint 9 | 27 Apr – 10 May
Safe | Sprint 10 | 11 May – 24 May
Safe | Sprint 11 | 25 May – 07 Jun
Safe | Sprint 12 | 08 Jun – 21 Jun
Safe | Sprint 13 | 22 Jun – 05 Jul
Safe | Sprint 14 | 06 Jul – 19 Jul
Safe | Sprint 15 | 20 Jul – 02 Aug
Safe | Sprint 16 | 03 Aug – 16 Aug
Safe | Sprint 17 | 17 Aug – 30 Aug
Safe | Sprint 18 | 31 Aug – 13 Sep
Safe | Sprint 19 | 14 Sep – 27 Sep
Safe | Sprint 20 | 28 Sep – 11 Oct
Safe | Sprint 21 | 12 Oct – 25 Oct
Safe | Sprint 22 | 26 Oct – 08 Nov
Safe | Sprint 23 | 09 Nov – 22 Nov
Safe | Sprint 24 | 23 Nov – 06 Dec
Safe | Sprint 25 | 07 Dec – 20 Dec
Safe | Sprint 26 | 21 Dec – 31 Dec
OneHire | Sprint 1 | 05 Jan – 18 Jan | [6 empty] | ▶ In Progress
OneHire | Sprint 2 | 19 Jan – 01 Feb
OneHire | Sprint 3 | 02 Feb – 15 Feb
OneHire | Sprint 4 | 16 Feb – 01 Mar
OneHire | Sprint 5 | 02 Mar – 15 Mar
OneHire | Sprint 6 | 16 Mar – 29 Mar
OneHire | Sprint 7 | 30 Mar – 12 Apr
OneHire | Sprint 8 | 13 Apr – 26 Apr
OneHire | Sprint 9 | 27 Apr – 10 May
OneHire | Sprint 10 | 11 May – 24 May
OneHire | Sprint 11 | 25 May – 07 Jun
OneHire | Sprint 12 | 08 Jun – 21 Jun
OneHire | Sprint 13 | 22 Jun – 05 Jul
OneHire | Sprint 14 | 06 Jul – 19 Jul
OneHire | Sprint 15 | 20 Jul – 02 Aug
OneHire | Sprint 16 | 03 Aug – 16 Aug
OneHire | Sprint 17 | 17 Aug – 30 Aug
OneHire | Sprint 18 | 31 Aug – 13 Sep
OneHire | Sprint 19 | 14 Sep – 27 Sep
OneHire | Sprint 20 | 28 Sep – 11 Oct
OneHire | Sprint 21 | 12 Oct – 25 Oct
OneHire | Sprint 22 | 26 Oct – 08 Nov
OneHire | Sprint 23 | 09 Nov – 22 Nov
OneHire | Sprint 24 | 23 Nov – 06 Dec
OneHire | Sprint 25 | 07 Dec – 20 Dec
OneHire | Sprint 26 | 21 Dec – 31 Dec
Spot | Sprint 1 | 05 Jan – 18 Jan | [6 empty] | ▶ In Progress
Spot | Sprint 2 | 19 Jan – 01 Feb
Spot | Sprint 3 | 02 Feb – 15 Feb
Spot | Sprint 4 | 16 Feb – 01 Mar
Spot | Sprint 5 | 02 Mar – 15 Mar
Spot | Sprint 6 | 16 Mar – 29 Mar
Spot | Sprint 7 | 30 Mar – 12 Apr
Spot | Sprint 8 | 13 Apr – 26 Apr
Spot | Sprint 9 | 27 Apr – 10 May
Spot | Sprint 10 | 11 May – 24 May
Spot | Sprint 11 | 25 May – 07 Jun
Spot | Sprint 12 | 08 Jun – 21 Jun
Spot | Sprint 13 | 22 Jun – 05 Jul
Spot | Sprint 14 | 06 Jul – 19 Jul
Spot | Sprint 15 | 20 Jul – 02 Aug
Spot | Sprint 16 | 03 Aug – 16 Aug
Spot | Sprint 17 | 17 Aug – 30 Aug
Spot | Sprint 18 | 31 Aug – 13 Sep
Spot | Sprint 19 | 14 Sep – 27 Sep
Spot | Sprint 20 | 28 Sep – 11 Oct
Spot | Sprint 21 | 12 Oct – 25 Oct
Spot | Sprint 22 | 26 Oct – 08 Nov
Spot | Sprint 23 | 09 Nov – 22 Nov
Spot | Sprint 24 | 23 Nov – 06 Dec
Spot | Sprint 25 | 07 Dec – 20 Dec
Spot | Sprint 26 | 21 Dec – 31 Dec
Pulse | Sprint 1 | 05 Jan – 18 Jan | [6 empty] | ▶ In Progress
Pulse | Sprint 2 | 19 Jan – 01 Feb
Pulse | Sprint 3 | 02 Feb – 15 Feb
Pulse | Sprint 4 | 16 Feb – 01 Mar
Pulse | Sprint 5 | 02 Mar – 15 Mar
Pulse | Sprint 6 | 16 Mar – 29 Mar
Pulse | Sprint 7 | 30 Mar – 12 Apr
Pulse | Sprint 8 | 13 Apr – 26 Apr
Pulse | Sprint 9 | 27 Apr – 10 May
Pulse | Sprint 10 | 11 May – 24 May
Pulse | Sprint 11 | 25 May – 07 Jun
Pulse | Sprint 12 | 08 Jun – 21 Jun
Pulse | Sprint 13 | 22 Jun – 05 Jul
Pulse | Sprint 14 | 06 Jul – 19 Jul
Pulse | Sprint 15 | 20 Jul – 02 Aug
Pulse | Sprint 16 | 03 Aug – 16 Aug
Pulse | Sprint 17 | 17 Aug – 30 Aug
Pulse | Sprint 18 | 31 Aug – 13 Sep
Pulse | Sprint 19 | 14 Sep – 27 Sep
Pulse | Sprint 20 | 28 Sep – 11 Oct
Pulse | Sprint 21 | 12 Oct – 25 Oct
Pulse | Sprint 22 | 26 Oct – 08 Nov
Pulse | Sprint 23 | 09 Nov – 22 Nov
Pulse | Sprint 24 | 23 Nov – 06 Dec
Pulse | Sprint 25 | 07 Dec – 20 Dec
Pulse | Sprint 26 | 21 Dec – 31 Dec

## Member Performance
Individual Member Performance — 2026
Track each member's progress, ratings, and feedback across sprints
# | Member | Team(s) | Role | Current Sprint Task | Progress % | Tech Lead Rating | Feedback / Notes | Achievements (YTD) | Areas to Improve
1 | Abdullah | OneWork | Tech Lead |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
2 | Faisal | Safe | Tech Lead |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
3 | Fatin | OneHire, Pulse | Developer
4 | Geena | AG ONE, OneWork | Tech Lead |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
5 | Hanis | OneHire, Pulse | Tech Lead
6 | Hema | Spot, Pulse | Developer
7 | Jawad | OneWork | Developer |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
8 | Kiritini | Safe | Developer |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
9 | Loc | Learn, Spot | Developer |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
10 | Logesh | OneHire | Tech Lead
11 | Majed | Spot, Pulse | Developer
12 | Nastaran | AG ONE, OneWork | Developer |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
13 | Rahmya | Pulse | Developer
14 | Ricky | Learn, Spot | Tech Lead |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
15 | Sharuti | OneHire | Developer
16 | Surya | Safe | Developer |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
17 | Than | Learn, Spot | Developer |  |  |  |  | Contributed to successful MVP launch of 4 products (AG ONE, OneWork, Learn, Safe) in 6 sprints
18 | Umeshawar | Pulse | Developer

## 2026 Targets
2026 Yearly Targets & Quarterly Milestones
High-level view of what each team must deliver per quarter
Team | Q1 Target (Jan–Mar) | Q1 Status | Q2 Target (Apr–Jun) | Q2 Status | Q3 Target (Jul–Sep) | Q3 Status | Q4 Target (Oct–Dec) | Q4 Status | Year-End Goal
AG ONE | MVP launch — platform, users, roles, tenants, SSO, permissions | ✅ Completed | Platform hardening, advanced admin, analytics | Not Started | Multi-product governance, API marketplace | Not Started | Enterprise features, scale & performance | Not Started | Full enterprise IAM platform with all products integrated
OneWork | MVP launch — employee mgmt, workflows, dashboards | ✅ Completed | Advanced workflows, integrations, reporting v2 | Not Started | Mobile support, AI-powered insights | Not Started | Enterprise scale, advanced automation | Not Started | Complete workforce management platform
Learn | MVP launch — courses, paths, assessments, certs | ✅ Completed | Advanced analytics, content marketplace | Not Started | Mobile learning, AI recommendations | Not Started | Enterprise LMS with full reporting | Not Started | Full-featured LMS with marketplace & analytics
Safe | MVP launch — policies, compliance, audit, risk matrix | ✅ Completed | Regulatory automation, advanced reporting | Not Started | Third-party integrations, automated alerts | Not Started | Enterprise compliance suite | Not Started | End-to-end compliance & risk management suite
OneHire | Requirements & design | Not Started | MVP development — job postings, applicant tracking | Not Started | MVP launch & post-launch improvements | Not Started | Advanced hiring analytics & integrations | Not Started | Full recruitment & applicant tracking system
Spot | Requirements & design | Not Started | Core city module development | Not Started | MVP launch — city management features | Not Started | Advanced features & scale | Not Started | City management module fully operational
Pulse | Requirements & design | Not Started | Survey builder & distribution engine | Not Started | MVP launch — survey analytics & dashboards | Not Started | AI-powered insights & benchmarking | Not Started | Complete employee engagement & survey platform

## How To Use
How To Use This Tracker
Quick guide for all stakeholders
Sheet | Purpose | Update Frequency | Who Updates
Team Overview | See all 7 teams, current sprint, status at a glance | Every sprint | Engineering Manager
Resource Allocation | View who belongs to which team, spot shared resources | When team changes | Engineering Manager
Project Roadmap | Track project start/end, achievements, next targets, alignment | Every sprint | Tech Leads
Sprint Tracker | Detailed sprint goals, outcomes, tech lead feedback, blockers | Every sprint | Tech Leads
Member Performance | Individual progress, ratings, achievements | Every sprint | Tech Leads
2026 Targets | Quarterly milestones and year-end goals per team | Quarterly | Engineering Manager
STATUS LEGEND
● ✅ Completed
● ▶ In Progress / On Track
● At Risk
● Blocked
● Not Started