## Release Dashboard
AG ONE — Release Dashboard 2026
All products at a glance • Last updated: 13 Apr 2026
📏 Standard: vMAJOR.MINOR.PATCH • Types: MVP ¦ Major ¦ Minor ¦ Hotfix ¦ Patch ¦ Sprint • Quarterly + hotfixes as needed
Product | Tech Lead | Latest Version | Latest Release | Release Date | Total Released | Hotfixes | Next Planned | Next Version | Target Date
AG ONE | Geena | v1.0.2 | AG ONE Hotfix 2 | 08 Apr 2026 | 3 | 2 | AG ONE Q2 Enhancement | v1.1.0 | May 2026
OneWork | Abdullah | v1.0.0 | OneWork MVP | 29 Mar 2026 | 1 | 0 | OneWork Q2 Enhancement | v1.1.0 | Jun 2026
Learn | Ricky | v1.0.0 | Learn MVP | 29 Mar 2026 | 1 | 0 | Learn Analytics | v1.1.0 | Jun 2026
Safe | Faisal | v1.0.0 | Safe MVP | 29 Mar 2026 | 1 | 0 | Safe Regulatory Auto | v1.1.0 | Jun 2026
OneHire | Logesh | — | — | — | 0 | 0 | OneHire Alpha | v0.1.0 | May 2026
Spot | Ricky | — | — | — | 0 | 0 | Spot Alpha | v0.1.0 | May 2026
Pulse | Hanis | — | — | — | 0 | 0 | Pulse Alpha | v0.1.0 | May 2026
TOTAL ACROSS ALL PRODUCTS |  |  |  |  | 6 | 2 | 19 releases planned

## AG ONE
AG ONE — Release History & Roadmap
Tech Lead: Geena • Released: 3 • Hotfixes: 2 • Planned: 3
Latest: v1.0.2 • Next: v1.1.0 (May 2026) • Total: 6 releases
✅ RELEASED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.0.0 | AG ONE MVP | MVP | 29 Mar 2026 | Sprint 6 | ✅ Released | Full IAM platform: Users, Roles, Tenants, SSO, Permissions, Audit, Assign Access
2 | v1.0.1 | AG ONE Hotfix 1 | Hotfix | 02 Apr 2026 | Sprint 7 | ✅ Released | SSO token refresh loop fix, role sync cache invalidation, tenant switching fix
3 | v1.0.2 | AG ONE Hotfix 2 | Hotfix | 08 Apr 2026 | Sprint 7 | ✅ Released | Audit log pagination, API key duplicate name validation, timezone fix
📋 UPCOMING / PLANNED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.1.0 | AG ONE Q2 Enhancement | Minor | May 2026 | Sprint 9–10 | 📋 Planned | Advanced user analytics, bulk role operations, enhanced audit dashboard
2 | v1.2.0 | AG ONE Multi-Product Admin | Minor | Jul 2026 | Sprint 13–14 | 📋 Planned | Multi-product admin console, cross-product role mapping, API marketplace v1
3 | v2.0.0 | AG ONE Enterprise | Major | Oct 2026 | Sprint 20–22 | 📋 Planned | Enterprise SSO (SAML+OIDC), advanced RBAC, white-label branding, scale

## OneWork
OneWork — Release History & Roadmap
Tech Lead: Abdullah • Released: 1 • Hotfixes: 0 • Planned: 3
Latest: v1.0.0 • Next: v1.1.0 (Jun 2026) • Total: 4 releases
✅ RELEASED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.0.0 | OneWork MVP | MVP | 29 Mar 2026 | Sprint 6 | ✅ Released | Employee mgmt, workflows, task mgmt, dashboards, reporting
📋 UPCOMING / PLANNED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.1.0 | OneWork Q2 Enhancement | Minor | Jun 2026 | Sprint 11–12 | 📋 Planned | Advanced workflow templates, email notifications, calendar integration
2 | v1.2.0 | OneWork Reporting v2 | Minor | Aug 2026 | Sprint 15–16 | 📋 Planned | Reporting v2 with charts, mobile-responsive, third-party integrations
3 | v2.0.0 | OneWork Enterprise | Major | Nov 2026 | Sprint 21–23 | 📋 Planned | AI-powered insights, advanced automation, enterprise scale

## Learn
Learn — Release History & Roadmap
Tech Lead: Ricky • Released: 1 • Hotfixes: 0 • Planned: 3
Latest: v1.0.0 • Next: v1.1.0 (Jun 2026) • Total: 4 releases
✅ RELEASED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.0.0 | Learn MVP | MVP | 29 Mar 2026 | Sprint 6 | ✅ Released | Courses, learning paths, assessments, certifications, progress tracking
📋 UPCOMING / PLANNED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.1.0 | Learn Analytics | Minor | Jun 2026 | Sprint 11–12 | 📋 Planned | Advanced analytics dashboard, learner recommendations, completion reports
2 | v1.2.0 | Learn Marketplace | Minor | Aug 2026 | Sprint 15–16 | 📋 Planned | Content marketplace, SCORM support, mobile-responsive learning
3 | v2.0.0 | Learn Enterprise | Major | Nov 2026 | Sprint 21–23 | 📋 Planned | AI recommendations, adaptive learning, full mobile app

## Safe
Safe — Release History & Roadmap
Tech Lead: Faisal • Released: 1 • Hotfixes: 0 • Planned: 3
Latest: v1.0.0 • Next: v1.1.0 (Jun 2026) • Total: 4 releases
✅ RELEASED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.0.0 | Safe MVP | MVP | 29 Mar 2026 | Sprint 6 | ✅ Released | Policies, compliance tracking, audit workflows, risk matrix, dashboards
📋 UPCOMING / PLANNED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v1.1.0 | Safe Regulatory Auto | Minor | Jun 2026 | Sprint 11–12 | 📋 Planned | Regulatory update automation, scheduled compliance checks, advanced reporting
2 | v1.2.0 | Safe Integrations | Minor | Sep 2026 | Sprint 17–18 | 📋 Planned | Third-party GRC integrations, automated alerts, evidence collection
3 | v2.0.0 | Safe Enterprise | Major | Dec 2026 | Sprint 24–26 | 📋 Planned | Enterprise compliance suite with AI-driven risk predictions

## OneHire
OneHire — Release History & Roadmap
Tech Lead: Logesh • Released: 0 • Hotfixes: 0 • Planned: 3
Latest: — • Next: v0.1.0 (May 2026) • Total: 3 releases
✅ RELEASED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
No releases yet — development in progress
📋 UPCOMING / PLANNED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v0.1.0 | OneHire Alpha | Sprint | May 2026 | Sprint 9–10 | 📋 Planned | Core job posting and applicant tracking features
2 | v0.5.0 | OneHire Beta | Sprint | Jun 2026 | Sprint 11–12 | 📋 Planned | Interview scheduling, candidate pipeline, basic reporting
3 | v1.0.0 | OneHire MVP | MVP | Jul 2026 | Sprint 13–14 | 📋 Planned | Full recruitment portal with applicant tracking and analytics

## Spot
Spot — Release History & Roadmap
Tech Lead: Ricky • Released: 0 • Hotfixes: 0 • Planned: 2
Latest: — • Next: v0.1.0 (May 2026) • Total: 2 releases
✅ RELEASED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
No releases yet — development in progress
📋 UPCOMING / PLANNED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v0.1.0 | Spot Alpha | Sprint | May 2026 | Sprint 9–10 | 📋 Planned | Core city module, location management
2 | v1.0.0 | Spot MVP | MVP | Sep 2026 | Sprint 17–18 | 📋 Planned | City management, geolocation features, admin dashboard

## Pulse
Pulse — Release History & Roadmap
Tech Lead: Hanis • Released: 0 • Hotfixes: 0 • Planned: 2
Latest: — • Next: v0.1.0 (May 2026) • Total: 2 releases
✅ RELEASED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
No releases yet — development in progress
📋 UPCOMING / PLANNED
# | Version | Release Name | Type | Date | Sprint | Status | What's Included / Highlights
1 | v0.1.0 | Pulse Alpha | Sprint | May 2026 | Sprint 9–10 | 📋 Planned | Survey builder, basic distribution
2 | v1.0.0 | Pulse MVP | MVP | Sep 2026 | Sprint 17–18 | 📋 Planned | Survey analytics, employee engagement dashboards, benchmarking

## Release Standard
Release Naming Standard & Versioning Policy
Share with all teams — standard format for naming and numbering releases
Component | Description | Example | Notes
Format | vMAJOR.MINOR.PATCH | v1.2.3 | Semantic versioning
MAJOR (X.0.0) | Breaking changes, major feature sets | v1.0.0 → v2.0.0 | Needs Director approval
MINOR (1.X.0) | New features, backward compatible | v1.0.0 → v1.1.0 | Quarterly cadence
PATCH (1.0.X) | Bug fixes, hotfixes | v1.0.0 → v1.0.1 | As needed
Release Type | Description | Frequency | Approval Required
MVP | First production release | Once per product | Director + Tech Lead
Major | Significant new features or breaking changes | 1–2 per year | Director + Tech Lead
Minor | New features, enhancements, backward compatible | Quarterly | Tech Lead
Hotfix | Critical production fix, expedited | As needed (urgent) | Tech Lead + post-mortem
Patch | Non-critical bug fixes | As needed | Tech Lead
Sprint | Pre-MVP iteration (alpha/beta) | Every 2 weeks | Tech Lead
Naming Pattern | Example | When to Use
[Product] MVP | AG ONE MVP | First production release
[Product] Q[N] Enhancement | AG ONE Q2 Enhancement | Quarterly minor release
[Product] Hotfix [N] | AG ONE Hotfix 1 | Emergency fix, numbered
[Product] [Theme] | AG ONE Enterprise | Major themed release
[Product] Alpha / Beta | OneHire Alpha | Pre-MVP sprint iterations